Individual Progress Report

Backend & Deployment Workstream — Sprint 7-8

Reporting Member: ME Ncube (22152725)

Role: Project Lead, Backend Lead and Deployment Owner

Reporting Period: Sprint 7-8 (Beyond MVP)

Submission Target: Thursday, 17 September 2026

# 1. My Progress — Where I Am Right Now

As Project Lead, my workstream covers deployment (website and Firebase), backend coordination, release identity, and final submission assembly.

Current status: In progress — deployment planning stage.

At this point, the application has not yet been deployed to a live environment. I am currently evaluating hosting options, with Google Cloud Platform as the preferred candidate, alongside alternative PHP-compatible hosting environments. Backend development across Sprints 1 to 6 is complete. The remaining work is to move that build into a released, accessible, and reproducible state.

Overall completion estimate for my role: Approximately 25 percent — planning complete, execution pending.

# 2. What I Have Done So Far

| # | Deliverable | Status |
| --- | --- | --- |
| 1 | Backend APIs developed across Sprints 1 to 6 (auth.php, sync.php, users.php, alerts.php, ai-insights.php, bill-calculator.php) | Complete |
| 2 | Live deployment environment identified (Google Cloud Platform under evaluation) | In progress |
| 3 | Firebase project configuration review | Started |
| 4 | .env migration plan drafted | Planned |
| 5 | Release identity plan (Sprint-8-Release Git tag) prepared | Planned |
| 6 | Daily stand-up structure defined | Complete |

# 3. How I Have Done It

## Development approach (Sprints 1 to 6)

- PHP and MySQL for backend logic and data persistence

- Firebase Realtime Database for live meter data streaming

- Firebase Authentication for secure user login and role management

- REST-style APIs under /api/ for frontend communication

## Deployment planning (Sprint 7-8)

- Evaluating Google Cloud Platform as the primary hosting environment due to its reliability, HTTPS support, and scalability

- Alternative options under consideration: cPanel-based shared hosting or a cloud virtual machine for simpler PHP deployment

- Firebase deployment will be handled from the Firebase Console (Authentication, Realtime Database, Storage, and Security Rules)

- Secrets will be moved into a .env file with a matching .env.example committed to the repository

## Coordination approach

- Daily stand-ups planned with each member reporting completed work, current work, and blockers

- Report sections assigned to ensure every member owns exactly 2 sections — 14 sections divided by 7 members

# 4. What Is Still Left

My remaining tasks before submission:

| # | Task | Deadline |
| --- | --- | --- |
| 1 | Finalise hosting platform (Google Cloud Platform or alternative) | Week 1 |
| 2 | Deploy the full stack (PHP, MySQL, Firebase) to live HTTPS | Week 1 |
| 3 | Move all secrets to .env; create .env.example | Week 1 |
| 4 | Configure Firebase production settings (Auth, Database, Storage, Rules) | Week 2 |
| 5 | Verify Firebase to PHP to MySQL end-to-end flow on live environment | Week 2 |
| 6 | Create and push Sprint-8-Release Git tag | Week 2 |
| 7 | Write RELEASE_NOTES.md | Week 2 |
| 8 | Compile final submission pack (15 items per Section 6 of brief) | Week 3 |
| 9 | Write Section 1 (Cover Page) and Section 2 (Executive Release Status) | Week 3 |

Estimated completion: End of Week 2 for deployment, end of Week 3 for submission pack.

# 5. How My Work Accommodates Sprint 7-8

Sprint 7-8 is a release-readiness sprint, not a feature-development sprint. My role is central to this.

| Sprint 7-8 Requirement | How I Address It |
| --- | --- |
| Deployed or installable MVP | Deploy website and Firebase to live HTTPS |
| Works outside developer's machine | Hosting on Google Cloud Platform or alternative |
| Production-like configuration, secrets excluded | .env migration and .env.example |
| Reproducible from README and release package | Release notes and submission pack |
| Stable Git tag matching the demo | Sprint-8-Release tag |
| Accessible to marker without private credentials | Public URL and documented test accounts |

Without my deployment workstream, the release cannot be evidenced. This is the critical path for Sprint 7-8.

Group Progress — Where We Are As a Team

# 1. Group Status Right Now

The team has completed the feature-development phase across Sprints 1 to 6. Sprint 7-8 work has now begun, focused on release readiness rather than new features.

Overall group release-readiness estimate: Approximately 30 percent — the application is built, but deployment, testing evidence, and documentation are still in progress.

# 2. What the Group Has Done

| Area | Status |
| --- | --- |
| 8 core features built (dashboard, history, alerts, billing, chatbot, admin, thresholds, properties) | Complete |
| Backend APIs implemented | Complete |
| Firebase integration | Complete |
| UI and UX designed (dark and light modes, responsive) | Complete |
| MySQL database schema designed | Complete |
| All 14 report sections assigned (2 per member) | Complete |

# 3. How the Group Has Done It

- Tech stack: PHP, MySQL, Firebase, JavaScript, Chart.js

- Workflow: Git-based with clear commit messages and daily stand-ups

- Division of labour: Every member owns exactly 2 report sections, 2 major deliverables, 2 supporting tasks, and produces 4 evidence files

- Sprint focus: Turn the built MVP into a released, tested, secure, and supportable release

# 4. What Is Still Left — Group-Wide

| Member | Outstanding Work |
| --- | --- |
| ME Ncube | Deploy website and Firebase; .env; Git tag; Sections 1, 2 |
| S Sibeko | Database backup and restore; architecture diagram; Sections 4, 6 |
| KM Selebano | Design system document; reflection compiler; Sections 3, 14 |
| NM Yingwani | UAT with 3 users; limitations document; Sections 9, 11 |
| ZE Mbangi | Test suite; Bug Register; rollback plan; Sections 8, 10 |
| B Sithole | Firebase listener audit; environment documentation; Sections 5, 12 |
| HN Bila | Security audit; POPIA; contribution table; Sections 7, 13 |

# 5. Sprint 7-8 Alignment (Group Level)

The group understands Sprint 7-8 as a release-readiness sprint. Every member's task list directly maps to a Sprint 7-8 requirement:

- Deployment — ME Ncube

- Integration evidence — S Sibeko and B Sithole

- Testing evidence — ZE Mbangi

- Security and POPIA — HN Bila

- User acceptance testing — NM Yingwani

- Design and documentation — KM Selebano

- Individual accountability — HN Bila (Section 13)

# 6. Immediate Group Actions

- ME Ncube — Finalise hosting (Google Cloud Platform or alternative) and begin deployment

- S Sibeko — Export schema and produce first database backup

- KM Selebano — Begin design system documentation

- NM Yingwani — Identify and recruit 3 UAT users

- ZE Mbangi — Open the Bug Register

- B Sithole — Start Firebase listener audit

- HN Bila — Run secret scan on repository

# Summary — My Section in One View

| Item | Status |
| --- | --- |
| Backend APIs | Complete |
| Website deployment | In progress — Google Cloud Platform under evaluation |
| Firebase deployment | Planned |
| .env migration | Planned |
| Git tag Sprint-8-Release | Planned |
| Release notes | Planned |
| Submission pack | Not started |
| Report Sections 1 and 2 | Draft pending |

My honest position: The code is ready. The deployment is the next step. I have identified Google Cloud Platform as the preferred hosting route and am preparing to execute the migration, Firebase configuration, and release evidence this sprint.